## Christos Panagi
Sprint 1
2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15
Done
Obtained familiarity with code base | Created function in database.py | Created html files | Connected html files with python | Sprint Review / retrospective
Divided tasks to team members | Created function in views.py |  |  | Commited task
To do
Sprint1: Task: Calculate first and last | Create html files | Connect html files with python
Create function in database.py | Connect html files with python
Create function in views.py
Create html files

## Sotiria Patroni
Sprint 1
2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15
Done
To do

## Costantinos Lebesis
Sprint 1
2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15
Done
familiarise with the code | initial tests | understand in depth Sotiria’s function |  | Sprint Review
run the test files | understanding the initial requirements | added more test |  | Push in gitlab the test function
understand the requirements |  | fixing initial tests
To do
| Analyse potential changes |  | Commit my tests
Fixing old test cases

## Yunwei Ge
Sprint 1
2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15
Done
run the source code | understand the logic and function of the source code | analyse the new requirement | test the new function(calculate the frist_last) | sprint review
find two tests failed |  | understand the logic of function written by Christos |  | submit the task
fix the bugs
pass the test
To do
understand the function of source code | analyse the new requirement | test for the requirement1(calculate first_last)
analyse the new requirement | test for the requirement1(calculate first_last)
test for the requirement1(calculate first_last)

## Zhenyun Lyu
Sprint 1
2017-11-09 | 2017-11-10 | 2017-11-11 | 2017-11-12 | 2017-11-13 | 2017-11-14 | 2017-11-15
Done
followed the instructions on blackboard to clone, run and test the code | get more familiar with the souce code | get full understand of the tasks in sprint1 | finished the test for the calculate_first_last function | Sprint Review / retrospective
went through the source code |  | analysed the requirements |  | Commited task
discussed the sprint1 with team menbers and got the divided work
fixed the existed errors and passed the tests
To do
get more familiar with the souce code | get full understand of the tasks in sprint1 | finished the test for the calculate_first_last function
get full understand of the tasks in sprint1 | analysed the requirements
analysed the requirements | finish the test for the new function: calculate_first_last
finish the test for the new function: calculate_first_last