## Backlog Report
Cartwright |  |  |  | Velocity: 1.0
Theme | ID | User Story | Acceptance Criteria | Sprint | Status | Points | Estimate | Days
Sprint-1 | Christos Panagi | As a developer I want to calculate the times an author appears first and last in publications So I can search for an author and display the information | a) Added ability to search for an author b) Added functionality about calculating number of 'firsts' c) Added functionality about calculating number of 'lasts' d) Display of the results | 1 | Done | 2.0 | 2 | 2.0
| Sotiria Patroni | As a developer I want to make all tables sortable So I can click the header and get sorted results | a) Added ability to sort in ascending order b) Added ability to sort in descending order | 1 | Done | 2.0 | 2 | 2.0
| Constantinos Lebesis | As a developer I want to create tests So I can test the sorting function | a) Verify that ascending order works b) Verify that ascending order works | 1 | Done | 1.0 | 1 | 1.0
| Zhenyun Lyu | As a developer I want to create tests So I can test that the function calculating first and last works | a) Created tests for calculating first b) Created tests for calculating last | 1 | Done | 1.0 | 1 | 1.0
| Yunwei Ge | As a developer I want to fix the bugs in the source code So I can it can pass the initial tests | a) Fixed the bugs in average.py | 1 | Done | 1.0 | 1 | 1.0
| Total for theme 'Sprint-1' |  |  | 7.0 points / 7.0 days
Sprint-2 | Christos Panagi | As a developer I want to create a function that returns every available information about an author So I can search for a given author and get the results | a) Added ability to search for an author b) Added functionality about calculating results c) Display of the results d) Used TDD | 2 | Done | 1.0 | 1 | 1.0
| Constantinos Lebesis | As a developer I want to test the function returning information about an author So I can verify that it works correctly | a) Added tests about function searching for author b) Used TDD | 2 | Done | 1.0 | 1 | 1.0
| Sotiria Patroni | As a developer I want to sort every author column by surname So I can click on the header and return sorted results | a) Added new function for preprocessing data b) Modified sorting function to work with surnames c) Added tests about new functionality d) Used TDD | 2 | Done | 2.0 | 2 | 2.0
| Yunwei Ge | As a developer I want to show the times authors appear as first, last and sole authors So I can get a list showing every author's statistics | a) Added functionality about sole author b) Modified function to work for every author c) Modified display to work an all authors | 2 | Done | 1.0 | 1 | 1.0
| Zhenyun Lyu | As a developer I want to create tests So I can make sure the function first,last,sole works correctly | a) Added tests about function calculating first,last,sole b) Used TDD | 2 | Done | 1.0 | 1 | 1.0
| Total for theme 'Sprint-2' |  |  | 6.0 points / 6.0 days
Sprint-3 | Christos Panagi | As a developer I want to show the number of times every author appears first,last and sole author by publication type | a) Added ability to show all authors b) Added functionality for calculating first,last,sole by publication type c) Display of the results using html d) Used TDD | 3 | Done | 1.0 | 1 | 1.0
| Constantinos Lebesis | As a developer I want to provide the ability to search for a substring and match authors' names and then show links to the statistics | a) Added functionality for searching for a substring in authors' names b)Provide the ability to click on a result and show statistics c)Used TDD | 3 | Done | 1.5 | 1.5 | 1.5
| Sotiria Patroni | As a developer I want to test that search for a substring works properly | a) Used TDD b) Added tests about new functionality | 3 | Done | 1.5 | 1.5 | 1.5
| Yunwei Ge | As a developer I want to show the number of first,last,sole author by publication type and number of coauthors and total number of publications by clicking on an author's name | a) Added functionality about total number of publications b) Added functionality for first, last, sole author by publication type c) Add functionality about coauthors d) Added functionality to click on an author's name and show the list e) Used TDD | 3 | Done | 1.0 | 1 | 1.0
| Zhenyun Lyu | As a developer I want to create tests So I can make sure the function total,first,last,sole,coauthors works correctly | a) Added tests about function calculating total,first,last,sole,coauthors b) Used TDD | 3 | Done | 1.0 | 1 | 1.0
| Total for theme 'Sprint-3' |  |  | 6.0 points / 6.0 days
Sprint-4 | Christos Panagi | As a developer I want to calculate the degrees of separation between authors | a) Added ability to calculate degrees of separation b) Ability to find author by scroll box c) Display of the results using html d) Used TDD | 4 | Done | 1.0 | 1 | 1.0
| Constantinos Lebesis | As a developer I want to create a good UI/UX for the website | a) Modifed existing html to create a unique UI/UX experience b) Provided a more user friendly exprerience | 4 | Done | 3 | 2 | 3
| Sotiria Patroni | As a developer I want to create a good UI/UX for the website
| Yunwei Ge | As a developer I want to create line charts in order to visualize important statistics from the database | a) Create a line graph for publication by year, author by year, publication by author and stats for author | 4 | Done | 1 | 1 | 1
| Zhenyun Lyu | As a developer I want to graphically display an author and his/hers co-authors | a) Ability to click on an author and visualize display the coauthors | 4 | Done | 1 | 1 | 1
| Total for theme 'Sprint-4' |  |  | 6.0 points / 6.0 days
Total for backlog 'Cartwright' |  |  |  | 25.0 points / 25.0 days

## Story List
Theme | ID | User Story | Acceptance Criteria | Status | Sprint | Points | Estimate | Days
Sprint-1 | DEV1 | As a developer I want to calculate the times an author appears first and last in publications So I can search for an author and display the information | a) Added ability to search for an author b) Added functionality about calculating number of 'firsts' c) Added functionality about calculating number of 'lasts' d) Display of the results | Done |  | 2.0 | 2.0 | 2.0
Sprint-1 | DEV2 | As a developer I want to make all tables sortable So I can click the header and get sorted results | a) Added ability to sort in ascending order b) Added ability to sort in descending order | Done |  | 2.0 | 2.0 | 2.0
Sprint-1 | DEV3 | As a developer I want to create tests So I can test the sorting function | a) Verify that ascending order works b) Verify that ascending order works | Done |  | 1.0 | 1.0 | 1.0
Sprint-1 | DEV4 | As a developer I want to create tests So I can test that the function calculating first and last works | a) Created tests for calculating first b) Created tests for calculating last | Done |  | 1.0 | 1.0 | 1.0
Sprint-1 | DEV5 | As a developer I want to fix the bugs in the source code So I can it can pass the initial tests | a) Fixed the bugs in average.py | Done |  | 1.0 | 1.0 | 1.0
Sprint-2 | SP21 | As a developer I want to create a function that returns every available information about an author So I can search for a given author and get the results | a) Added ability to search for an author b) Added functionality about calculating results c) Display of the results d) Used TDD | Done |  | 1.0 | 1.0 | 1.0
Sprint-2 | SP22 | As a developer I want to test the function returning information about an author So I can verify that it works correctly | a) Added tests about function searching for author b) Used TDD | Done |  | 1.1 | 1.0 | 1.0
Sprint-2 | SP23 | As a developer I want to sort every author column by surname So I can click on the header and return sorted results | a) Added new function for preprocessing data b) Modified sorting function to work with surnames c) Added tests about new functionality d) Used TDD | Done |  | 2.1 | 2.1 | 2.0
Sprint-2 | SP24 | As a developer I want to show the times authors appear as first, last and sole authors So I can get a list showing every author's statistics | a) Added functionality about sole author b) Modifed function to work for every author c) Modified display to work an all authors | Done |  | 1.0 | 1.0 | 1.0
Sprint-2 | SP25 | As a developer I want to create tests So I can make sure the function first,last,sole works correctly | a) Added tests about function calculating first,last,sole b) Used TDD | Done |  | 1.0 | 1.0 | 1.0
Sprint-3 | Christos Panagi | As a developer I want to show the number of times every author appears first,last and sole author by publication type | a) Added ability to show all authors b) Added functionality for calculating first,last,sole by publication type c) Display of the results using html d) Used TDD | Done |  | 1.0 | 1.0 | 1.0
Sprint-3 | Constantinos Lebesis | As a developer I want to provide the ability to search for a substring and match authors' names and then show links to the statistics | a) Added functionality for searching for a substring in authors' names b)Provide the ability to click on a result and show statistics c)Used TDD | Done |  | 1.5 | 1.5 | 1.5
Sprint-3 | Sotiria Patroni | As a developer I want to test that search for a substring works properly | a) Used TDD b) Added tests about new functionality | Done |  | 1.5 | 1.5 | 1.5
Sprint-3 | Yunwei Ge | As a developer I want to show the number of first,last,sole author by publication type and number of coauthors and total number of publications by clicking on an author's name | a) Added functionality about total number of publications b) Added functionality for first, last, sole author by publication type c) Add functionality about coauthors d) Added functionality to click on an author's name and show the list e) Used TDD | Done |  | 1.0 | 1.0 | 1.0
Sprint-3 | Zhenyun Lyu | As a developer I want to create tests So I can make sure the function total,first,last,sole,coauthors works correctly | a) Added tests about function calculating total,first,last,sole,coauthors b) Used TDD | Done |  | 1.0 | 1.0 | 1.0
Sprint-4 | Christos Panagi | As a developer I want to calculate the degrees of separation between authors | a) Added ability to calculate degrees of separation b) Ability to find author by scroll box c) Display of the results using html d) Used TDD | Done |  | 1.0 | 1.0 | 1.0
Sprint-4 | Constantinos Lebesis | As a developer I want to create a good UI/UX for the website | a) Modifed existing html to create a unique UI/UX experience b) Provided a more user friendly exprerience | Done |  | 3 | 2 | 3
Sprint-4 | Sotiria Patroni | As a developer I want to create a good UI/UX for the website
Sprint-4 | Yunwei Ge | As a developer I want to create line charts in order to visualize important statistics from the database | a) Create a line graph for publication by year, author by year, publication by author and stats for author | Done |  | 1 | 1 | 1
Sprint-4 | Zhenyun Lyu | As a developer I want to graphically display an author and his/hers co-authors | a) Ability to click on an author and visualize display the coauthors | Done |  | 1 | 1 | 1